## Product Backlog
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US001 | As a doctor, I want to upload medical images so that the AI can enhance and process them. | Must Have | Image upload module | Frontend Team | Completed
Sprint 1 | Sprint 1 | US002 | As an AI engineer, I want to integrate the image enhancement model so that doctors receive clearer visual outputs. | Must Have | Model availability | Backend Team | Completed
Sprint 2 | Sprint 2 | US003 | As a clinician, I want to enter patient clinical notes so that the AI can generate structured medical summaries. | Must Have | Text input form | Frontend Team | Completed
Sprint 2 | Sprint 2 | US004 | As an AI developer, I want the system to automatically generate ICD-10 codes so that diagnoses are standardized. | Should Have | Clinical summary output | Backend Team | Completed
Sprint 3 | Sprint 3 | US005 | As a UI/UX designer, I want to create a clean and simple interface so that doctors can easily use the system. | Must Have | Backend API | Frontend Team | Completed
Sprint 3 | Sprint 3 | US006 | As a backend engineer, I want to build API endpoints for image enhancement, report generation, and ICD-10 inference. | Must Have | AI model integration | Backend Team | Completed
Sprint 4 | Sprint 4 | US007 | As a DevOps engineer, I want to deploy the entire application online so that it can be accessed from any device. | Could Have | Frontend & backend integration | DevOps Team | Completed
Sprint 4 | Sprint 4 | US008 | As a QA tester, I want to validate all modules so that the system is reliable and error-free. | Should Have | Fully integrated system | QA Team | Completed
Sprint 4 | Sprint 4 | US009 | As a technical writer, I want to prepare complete project documentation so that stakeholders can understand the system. | Must Have | Finalized features | Documentation Team | Completed

## Sprint_Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
US001 | T1 | Design and implement image upload module | 2025-09-22 | 2025-09-23 | Frontend1 | UI Development | Done | 6 | bar: Day 1 to Day 2
US001 | T2 | Integrate AI image enhancement model API | 2025-09-22 | 2025-09-24 | Backend1 | Model Integration | Done | 10 | bar: Day 2 to Day 4
US002 | T3 | Develop clinical text input & preprocessing module | 2025-09-22 | 2025-09-25 | Frontend2 | UI Development | Done | 12 | bar: Day 3 to Day 6
US003 | T4 | Implement ICD-10 classification pipeline | 2025-10-07 | 2025-10-10 | Backend2 | AI Inference | Done | 8 | bar: Day 4 to Day 6
US004 | T5 | Create output UI for enhanced images and reports | 2025-10-07 | 2025-10-10 | Frontend3 | UI/UX | Done | 10 | bar: Day 5 to Day 8
US005 | T6 | Deploy frontend and backend | 2025-10-21 | 2025-10-23 | DevOps | Deployment | Done | 8 | bar: Day 6 to Day 9

## Standup_Meeting
Column1 | Column2 | Column3 | Column4
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Image enhancement model output blurry for low-light radiology images | Added preprocessing (contrast normalization + histogram equalization)
Sprint 1 | Day 4 | Backend API returning slow responses during image enhancement inference | Enabled model warm‑loading and optimized CUDA batch size
Sprint 2 | Day 3 | Clinical summary generation occasionally missing key symptoms from clinician notes | Improved text preprocessing and added medical keyword extraction
Sprint 2 | Day 5 | ICD‑10 code prediction giving low‑confidence outputs for multi‑disease cases | Added confidence thresholding and fallback multi‑label classification rule
Sprint 3 | Day 2 | Frontend UI failing to display enhanced images due to incorrect base64 formatting | Fixed decoder handling and updated API response structure
Sprint 3 | Day 4 | Users reporting long wait time when summary + ICD‑10 tasks run together | Separated tasks into async workers using queue-based processing
Sprint 4 | Day 1 | Deployment build failing because of incompatible Python dependency versions | Pinned stable versions and rebuilt using isolated virtual environment
Sprint 4 | Day 3 | Doctors unable to upload large DICOM files on UI | Increased upload size limit and implemented progressive uploading

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2025-09-22 | 2025-10-06 | Backend Team | Define clear preprocessing pipeline for medical images | Running inference without validating image quality | Synchronizing frequently with AI team | Created standardized preprocessing workflow with documentation
2 | 2 | 2025-10-07 | 2025-10-20 | AI Team | Validate clinical summaries with sample clinician feedback | Using generic summarization prompts | Iteratively tuning the summarization model | Developed medically‑aligned prompt templates and validation rules
3 | 3 | 2025-10-21 | 2025-11-03 | AI + Backend Team | Optimize ICD‑10 model with confidence scoring | Using single-label predictions only | Monitoring inference logs for model accuracy | Implemented multi‑label ICD‑10 inference with thresholding
4 | 4 | 2025-11-04 | 2025-11-17 | Frontend + Backend | Coordinate API–UI integration earlier in the sprint | Waiting until end of sprint to integrate enhancement outputs | Maintaining consistent API–UI contract | Scheduled mid‑sprint integration checkpoints
5 | 5 | 2025-11-18 | 2025-11-22 | DevOps + Full Team | Automate deployment and testing workflows | Manual environment testing | Continuous monitoring of deployed system | Added CI/CD with auto‑tests, improved deployment reliability