## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Sri Varsan | 24/09/2025 | OCR not extracting Patient_ID | Sprint 1 | Backend Team | Functional | Improved preprocessing, added configs | 23/09/2025 | Closed | Improved
2 | Vishal Kumar | 2025-09-10 | ICD-10 mapping inconsistencies | Sprint 2 | AI Team | Algorithmic | Improved ICD-10 matching | 2025-08-10 | Closed | Better accuracy
3 | Atharv Phatak | 2025-11-10 | MRI images not displaying | Sprint 2 | Frontend Team | UI/Integration | Fixed paths + API | 2025-10-10 | Closed | Verified
4 | Divya Prabhashree | 13/10/2025 | MRI caption repetitive | Sprint 2 | AI Team | Model Training | Fixed decoding | 2025-12-10 | Closed | Stable output
5 | Swarup r. Mohanty | 23/10/2025 | Duplicate Patient_ID | Sprint 3 | Backend | Logic | UUID + duplicate rules | 22/10/2025 | Closed | Unique IDs
6 | Isha Khairnar | 26/10/2025 | MRI uploads rejected | Sprint 3 | Frontend | UI/Validation | MIME validation | 25/10/2025 | Closed | Working
7 | Venkata Sunil | 28/10/2025 | Slow summarization pipeline | Sprint 3 | AI Team | Performance | GPU + batching | 27/10/2025 | Closed | Faster
8 | Sathyadev Nayak | 2025-06-11 | Reports not updating | Sprint 4 | Backend | Integration | Remapped schema | 2025-05-11 | Closed | Synced
9 | Swetha S. | 2025-08-11 | ICD-10 missing in reports | Sprint 4 | Frontend | Functional | Fixed binding | 2025-07-11 | Closed | Correct output
10 | Aarti Kumari | 2025-11-11 | MRI images missing | Sprint 4 | Backend | UI | Fixed PIL rendering | 2025-10-11 | Closed | Shows correctly